## Slide 1
STATUS ICG/CARIBE EWS IMPLEMENTATION PLAN AND GLOBAL KPI
MARY LUZ RENGIFO BUITRAGO (COL)
ICG/CARIBE TT Chair Future Goals and Key Performance Indicators
26 April 2023, ICG/Caribe XVI

## Slide 2: STATUS IMPLEMENTATION PLAN
 | WG | GOALS
1. | MONITORING AND DETECTION | 13
2. | HAZARD AND RISK ASSESSMENT | 14
3. | TSUNAMI SERVICES | 8
4. | PUBLIC AWARENESS, EDUCATION AND RESILIENCE | 12
 | TOTAL | 47
STATUS | PENDING | ONGOING | COMPLETED
MONITORING AND DETECTION | 7 | 4 | 2
HAZARD AND RISK ASSESSMENT | 5 | 4 | 5
TSUNAMI SERVICE | 3 | 4 | 1
PUBLIC AWARENESS EDUCATION | 5 | 3 | 4
TOTAL | 20 | 15 | 12
Chart: STATUS IMPLEMENTATION PLAN
| PENDING | ONGOING | COMPLETED
 | 20 | 15 | 12
Matrix status implementation plan available here

## Slide 3: 1. MONITORING AND DETECTION
TARGET: At risk coastal communities of all countries receive timely, accurate, reliable and effective warnings for all types of tsunamis and other coastal hazards. (Total goals13)
Chart: 
| PENDING | ONGOING | COMPLETED
MONITORING AND DETECTION | 7 | 4 | 2
WG 1 | PENDING | ONGOING | COMPLETED
SHORT TERM 2019 | 2 | 1 | 1
MEDIUM TERM 2021 | 3 | 1 | 0
LONG TERM 2023 | 2 | 2 | 1
TOTAL | 7 | 4 | 2

## Slide 4: 2. HAZARD AND RISK ASSESSMENT
TARGET: All countries have assessed the tsunami and other coastal risk to their coastlines. (Total goals 14)
Chart: 
| PENDING | ONGOING | COMPLETED
HAZARD AND RISK ASSESSMENT | 5 | 4 | 5
WG 2 | PENDING | ONGOING | COMPLETED
SHORT TERM 2019 | 2 | 3 | 2
MEDIUM TERM 2021 | 1 | 1 | 2
LONG TERM 2023 | 2 | 0 | 1
TOTAL | 5 | 4 | 5

## Slide 5: 3. TSUNAMI SERVICES
TARGET: Technology and communications platform for alerts, and Protocols for end to end community based communication and dissemination of warnings and feedback between agencies of the countries and PTWC. (Total goals 8)
Chart: 
| PENDING | ONGOING | COMPLETED
TSUNAMI SERVICES | 3 | 4 | 1
WG 3 | PENDING | ONGOING | COMPLETED
SHORT TERM 2019 | 1 | 2 | 0
MEDIUM TERM 2021 | 2 | 0 | 0
LONG TERM 2023 | 0 | 2 | 1
TOTAL | 3 | 4 | 1

## Slide 6: 4. PUBLIC AWARENESS, EDUCATION AND RESILIENCE
TARGET: At risk coastal communities of all countries, ready to respond effectively to tsunami threat and other coastal hazards (Total goals 12 )
Chart: 
| PENDING | ONGOING | COMPLETED
PUBLIC AWARENESS EDUCATION | 5 | 3 | 4
WG 4 | PENDING | ONGOING | COMPLETED
SHORT TERM 2019 | 1 | 1 | 2
MEDIUM TERM 2021 | 2 | 1 | 2
LONG TERM 2023 | 2 | 1 | 0
TOTAL | 5 | 3 | 4

## Slide 7: RECOMMENDATIONS
It is necessary a review from the WG of the implementation plan, based on current conditions, the goals of the ODTP and the global KPI for its rethink.
2. Prioritize activities to execute the plan more efficiently.

## Slide 8
GLOBAL GOALS AND PERFORMANCE MONITORING
Sendai Framework for Disaster Risk Reduction 2015-2030
United Nations Decade of Ocean Sciences for Sustainable Development – A Safe Ocean – Daft Ocean Decade Tsunami Program
IOC Tsunami Programme – people centred EWS; aims at reducing the loss of lives and livelihoods from worldwide tsunamis; assess tsunami risk; educate communities at risk implement; multi-hazard disaster reduction strategies.
Tsunami Ready – enabling communities to reach a high level of tsunami resilience

## Slide 9
GLOBAL GOALS AND TARGETS
Goals:
  GOAL 1: Understanding and Managing Tsunami Hazard and Risk
  GOAL 2: Tsunami Detection, Warning & Dissemination
  GOAL 3: Enhancing tsunami preparedness for effective community response
  GOAL 4: Tsunami event response and recovery
  GOAL 5: Global ocean coordination, cooperation and partnerships (Working Group/ICG Leaders Only)

## Slide 10
IOC GLOBAL PERFORMANCE MONITORING FRAMEWORK
Develop a consistent global performance monitoring framework, which includes data collection tools/questionnaire and reporting formats.
  Final draft available

## Slide 11
Expectations are to:
  Monitor and evaluate against this framework
  Provide yearly reports via the annual ICG meeting structures
  Prioritize actions in order to improve tsunami risk management in each ICG
  Participate in annual TOW’s meetings/workshops on global basin assessments, presenting gaps, opportunities and improvements regarding the framework evaluation.
EXPECTATIONS

## Slide 12
ONGOING ACTIONS
Coordination with UNESCO COI to develop ToR for supporting the web portal - In progress
Development questionnaire to be published in the web portal Web-based Portal
GLOBAL FRAMEWORK ACCESS
QUESTIONS | SCORE FOR AUTOMATIC CALCULATION
Does your country developed a methodology and supporting guidance for modeling and designation tsunami inundation and evacuation zones? | Score %
No | 25
The methodology is in development | 50
It has the methodology, but it is not supporting guidance | 75
It has the methodology and the guidance | 100
    Hosted on IOC site
    Algorithm functionality
    Real-time graphs
    Fair and ethical
    Easy, accessible and simple (yet comprehensive) National, ICG and Global reporting

## Slide 13
!GRACIAS!
THANKS !
STATUS ICG/CARIBE EWS IMPLEMENTATION PLAN AND GLOBAL KPI