## Sheet1
Action Monitoring SCS WG
No | Action | Refference | Lead | Deadline | Status | Comment
1 | Requests the IOC Secretariat to make an announcement to all Member States’ National Tsunami Warning Center (NTWC), Tsunami National Contacts (TNC) and Tsunami Warning Focal Points (TWFP) of WG-SCS the International Staff Programme to host seconded experts at the South China Sea Tsunami Advisory Center (SCSTAC) from the Member States of the WG-SCS in 2025, with the travel and local expenses covered by the National Marine Environmental Forecasting Center (NMEFC) | ICG/PTWS WG-SCS-XII | Secretariat and NMFEC |  | Completed | The seconded expert in NMFEC has been conducted since 20th October 2025, and will be ended at 20th December 2025
2 | Requests the Task Team on Capacity Development and Services to promote the conduct of trainings related to the indicators in the TRRP by engaging more experts from WG-SCS to serve as resource persons or trainers for this activity; | ICG/PTWS WG-SCS-XII | Task Team on Capacity Development |  | Not yet completed | Started to plan on December 12. Training/Workshop on TR will be conducted online on December 2025
3 | Requests the SCSTAC to make ready the draft revised User’s Guide by December 2024 for the Chair of the WG-SCS to circulate it to Member States for review by January 2025 | ICG/PTWS WG-SCS-XII | SCS TAC, Circulated to the member by Chair | 2025-01-01 | Completed | had been reviewed by the chair and circulated to the member states
4 | Strongly encourages Member States to contribute to capacity development activities such as identification of resource persons or experts to conduct roving seminars/workshops/technical visits to promote exchanges and experience sharing among Member States in order to achieve the goal of tsunami resilience in a sustainable way; | ICG/PTWS WG-SCS-XII | MS
5 | Strongly encourages the Member States of the WG-SCS to share more seismic and sea level stations data for tsunami warning purposes in accordance with the IOC Oceanographic Data Exchange Policy to further enhance the tsunami warning capability in the South China Sea region in order to be able to meet this target; | ICG/PTWS WG-SCS-XII | MS |  | A member had shared the sea level data stations | Indonesia had shared 21 sea level stations, published on the IOC Website
6 | Requests the Member States of the WG-SCS to regularly update information on NTWC, TNC and TWFP with IOC Secretariat following the established procedures; | ICG/PTWS WG-SCS-XII | MS |  |  | Need confirmation from the Secretariat related to updated information