Component / Task team:

Observations Coordination Group (OCG)

Report submitted by:

Emma Heslop, Juliet Hermes, Champika Gallage, Mathieu Belbeoch, Kevin Obrien, Ann Christine Zinkann, Nelly Florida Riama, Abed El Rahman Hassoun

Date submitted:

20/03/2026

Report on workplan progress

Introduction/Background

Including links to relevant documents, mandates etc.

The Observations Coordination Group (OCG) is the coordinating body for the GOOS observing networks, responsible for coordinating across requirements, aligning data flows, observing platform metadata, and cross-network collaboration in support of GOOS objectives across a range of areas. Overall the Observation Coordination Group (OCG) works to efficiently operate, maintain, coordinate and integrate a comprehensive in-situ global ocean observing system. It targets work around 8 foci: Requirements, Observing Advances, Standards and Best Practices, Data Management, OceanOPS, Metrics, with environmental stewardship and capacity development considered at network level. The OCG now coordinates across 17 global observing networks - 13 mature and 4 emerging, and it maintains close collaboration with WMO INFCOM. Key current actions include: advancing data infrastructure for GOOS networks (Data Implementation Strategy); coordinating OceanOPS services to networks; supporting the GOOS Status Report; and facilitating observing network integration and coordination with WMO/WIGOS systems. This report covers OCG workplan progress for the period leading to GOOS SC-15, drawing on outcomes from OCG Executive discussions of 17 March 2026. Note: This report does not contain updates from across the individual networks, as these are typically provided for the OCG annual meeting, next will be OCG-17 in May 2026.

Updates on work

Progress against workplan: The OCG continued implementing its 2025-2026 workplan key progress to highlight incudes: - Requirements: Supported finalization of the WMO Rolling Review of Requirements (RRR) Statement of Guidance (SOG) for Ocean with full network participation - this will be released by WMO in April 2026 - WIGOS Integration: Provided strategic input into the WIGOS 2050 Vision. - Data and Metadata: The task team spent 2025 establishing foundational data infrastructure for GOOS. Key achievements included conducting a network survey to understand metadata practices, developing the minimum metadata requirements (Passport) across networks (unique WIGOS IDs for all platforms, WIGOS/OSCAR compliant, controlled vocabulary via BODC NVS), a network data survey to understand metadata practices, mapping data endpoints across networks, and introducing important discussions on data provenance and licensing. Networks as managed vocabulary: to be implemented at NODC. - BioEco Panel Engagement: Sustained dialogue with the GOOS BioEco Panel (including OBIS) to align the GOOS minimum metadata passport with biological metadata requirements and identified collaborative pilots - specific projects for integrated data delivery, including CalCOFI and the animal tracking network (linked to AniBOS). - Network Onboarding: Successfully onboarded a new network (SUN Fleet), bringing OCG membership to 17 global networks (13 mature and 4 emerging – network summary). - OCG Leadership: Successfully recruited and onboarded new Chair - Juliet Hermes and new Vice Chairs- Abed El Rahman Hassoun (Standards and Best Practices) and Nelly Florida Riama (WMO) - Metrics: Emerging network and mature network status defined against the OCG Network Attributes and a subset trackable metrics are now defined to show progress to reaching maturity for networks -- piloted for OCG-17 - GOOS endorsement of new Practices: e.g. VOS and others under development, strong download of GOOS endorsed practices (see figure at end) OceanOPS - Hosting Stability: Secured a 5-year hosting contract with Ifremer to ensure OceanOPS operational stability and data unification synergies. - Service Level Agreements (SLAs): Rationalized services to networks through new SLAs, aligning support with allocated resources and increasing accountability. - 10K Ships Initiative: Advanced the public-private framework to scale up ship-based observations by championing the shipping industry as a multidisciplinary GOOS partner. - Reporting Capacity: Improving reporting capacity (GOOS Yearly Status Report) - impact is visibility for GOOS integrated system, challenges and opportunities - OceanOPS 5-Year Strategy: internal workshop and planning for stakeholder interviews and workshop to deliver new forward looking OceanOPS 5-Year Strategy by end 2026 Top 5 outcomes from the last year, and the impact for GOOS: - 17 GOOS Observing networks: impact is GOOS consolidated as core global coordinator, with new networks developing impact in new areas and with new partners - Implementation Data Strategy: key outcomes in 2025/2026 are the minimum metadata Passport, global end point strengthening (WIS 2.0 compliant) - impact is progress towards a standardized, globally interoperable data architecture, machine-to-machine metadata harvesting, and data discoverability - delivering FAIR - OceanOPS Service Level Agreements - impact is stability, accountability, fair support for networks and free baseline - rationalizing services to networks/aligning resources - Metrics: key to tracking data delivery, network resilience, achievement towards targets, network ‘health’ and reporting (Status Report) - 10K ships public private framework - 2025 launch and 2026 workshop with first shipping champion - impact visibility across the shipping industry, more surface observations within 2 years

Looking ahead

Prioritised deliverables (2026-2027) Data TT 2026 Priorities - Data Strategy & Data Delivery: GitHub workspace for collaboration, prioritize machine-to-machine metadata integration into OceanOPS, implement ERDDAP services at data endpoints. Trial the first OCG (consolidated) ERDDAP (Ifremer) enabling cross network data discovery and harvest - OCG ➔ ICG Transition: Manage the evolution from OCG to the proposed Infrastructure Coordination Group (ICG). - Develop integrated system view: Viewing the observing system by EOV, develop pilot and set requirements for the work ahead at OCG-17. Design towards assessment of system against requirements - Strengthening connections with the modelling community - GOOS Minimum Metadata Passport: Standardise metadata requirements for platform discoverability across GOOS (OCG and BuioEco data flows) - Data Architecture: Finalise architecture across OCG and the BioEco Panel, specifically addressing uncertainty and representation for streamlined data flows. Expected outcomes for GOOS - Automated Data Flows: Improved machine-to-machine flows across networks, reducing manual reporting burdens and increasing data discoverability via WIS 2.0-compliant endpoints and IODE ODIS, other as required - Unified Access: A federated OCG ERDDAP service providing a unified access point for modeling communities to utilize cross-network ocean data at scale. - Enhanced Assessment: Increased capacity for OCG to assess EOV coverage versus requirements, and network status and health, supporting rigorous reporting for member states and policymakers.

Considerations for the GOOS SC

- Considerations for the GOOS SC Resource Realities: Note that the proposed ICG structure requires significant staff increases (6 additional FTEs) to handle the expanded coordination mandate. OCG requires additional support with 17 networks. - National Coordination: GOOS should focus on global coordination while leaving national and coastal network management to individual Member States.

Proposed action/decision - Steering Committee …