Component / Task team:

GOOS Ocean Observing Co-Design Programme

Report submitted by:

GOOS Ocean Observing Co-Design Programme

Date submitted:

20/03/2026

Report on workplan progress

Introduction/Background

Including links to relevant documents, mandates etc.

Ocean Observing Co-Design Programme The GOOS Ocean Observing Co-Design Programme is one of the three GOOS Programmes established under the UN Decade of Ocean Science for Sustainable Development, with the aim of transforming GOOS in key areas. Following the mandate discussed at SC-14, the programme advances a transformational shift, evolving GOOS from a purely platform-led infrastructure to also incorporate co-designed systems that directly link observations, modeling, and users to build fit-for-purpose observing system enhancements that provide impact and tangible outcomes that meet users requirements. The programme directly responds to the GOOS 2030 Strategy and the Strategy Roadmap through its four key objectives: - Integrate ocean observing and prediction based upon co-design to support a sustainable ocean and society in ways that are measurably better. - Bolster ocean observing and information appreciably through transformative co-design with key users - Establish the international capability to undertake co-design processes, including infrastructure needs, leading to a more impactful observing system. - Consider new approaches and technology across all elements of the co-design programme. The programme chose to apply co-design principles within selected application areas of high societal need, called Exemplars, to advance ocean observing and put co-design into practice, whilst advancing co-design knowledge and process across the programme. The current Exemplars are: Tropical Cyclones, Ocean Carbon, Marine Heatwaves, Boundary Currents, and Storm Surge. In the last four years, the Co-Design programme has consistently applied a co-design approach through its Exemplars, turning the concept into practice. The programme is executed by a global team from 19 countries and 35 institutions and has been supported by GOOS and its co-sponsor World Meteorological Organization (WMO) to ensure observing requirements are directly linked to operational forecasting needs across weather and climate.

Updates on work

Progress against workplan: In 2025, the Programme moved from design to active implementation, following the 2025-2026 Work Plan adopted during the Miami Strategy Meeting (2025). Building on the Exemplar Maturity framework presented at SC-14, several use cases have successfully transitioned from Phase 1 (Engagement) to Phase 2 (Pilot Activity). Notable progress was made across all active Exemplars and in distilling the co-design learning into a Vision Paper. This vision paper defines 10 key lessons we have learnt so far in implementing co-design principles across user communities, ocean observing, modeling and data communities and different geographical regions. It articulates 5 actions that are key to enable co-design to make a paradigm shift for sustained ocean observations that enable the 1 vision of deep societal support of ocean observations. - Co-Design Strategy and Planning Meeting 2025 - 2025–2026 Work Plan - Co-Design Vision for Policy Makers Top 5 outcomes from the last year, and the impact for GOOS: - Co-Design Vision for Policy Makers: Draft Paper prepared for OSM26, providing a blueprint for integrating co-design into the value chain of observing, modelling, and user services and into GOOS. - Transition to Operational Pilots (Tropical Cyclones): Successfully launched the 2025 Caribbean Glider Mission in collaboration with IOCARIBE and CIMH, demonstrating transboundary data delivery for hurricane intensification forecasts 2025 Caribbean Glider Mission in collaboration with IOCARIBE - Development of external funding resources: (1) Ocean Carbon Exemplar: Secured Horizon Europe funding to establish a regional consortium in the North Atlantic, moving the Carbon Exemplar into an active implementation phase for integrated carbon observations; (2) Submission of two FUST funding proposals for Boundary Currents Exemplar and Marine Heatwaves Exemplar - Multidisciplinary Data Delivery: (BioEco) Reinvigorated the ideas for an ocean health delivery area with a BioEco/AniBOS Exemplar to support mitigation of vessel strikes and inform conservation planning, demonstrating the integration of biological observations into co-designed services; - Marine Heatwave leadership reformed and two exemplar regions (Australia and Caribbean Seas) aligned with GOOS Regional Alliances - Joint Co-Design and SynObs session at OSM26 - Publication of the Boundary Currents Workshop Report, documenting outcomes from the 2024 Agulhas–Benguela co-design workshop

Looking ahead h

Prioritised deliverables (2026-2027) - Support investment opportunities and advocate for observing system development at national and regional levels working through Exemplar activities, GOOS GRAs and Ocean Decade activities - using the Vision Paper - SynObs International Workshop (August 2026): Lead co-design sessions in Mutsu to refine cross-network observing system designs based on Exemplar requirements. - Scaling Regional Pathways: Develop implementation pathways that link observing activities to societal applications and decision-making needs in cyclone-prone regions (Caribbean and Pacific Islands) - ‘blue print’ for value chain in multi regions paper - Maintain and build momentum of Boundary Current, Marine heatwave, and AniBOS Exemplars by moving from Phase I or Phase 2 to Phase 3 (implementation stage). - Secure multi-year financial support to employ a technical support officer Expected outcomes for GOOS - Observing systems capable of delivering multi sectoral services spanning early warning and ecosystem management. - A scalable "blueprint" for regional co-design that can be replicated across GOOS Regional Alliances (GRAs)

Considerations for the GOOS SC

- Create and endorse an Expert Team on Co-Design - ETCODE - that works on a rolling set of Exemplars to streamline user-driven requirements and engage regional design - Secure resourcing to employ a dedicated technical support officer.

Proposed action/decision - Steering Committee …